| ## HUMAN CAPITAL INVESTMENT OPERATIONAL PROGRAMME 2007-2013 |  |
| --- | --- |
| ### Priority: | ##### TECHNICAL ASSISTANCE |
| ### Theme/Dimension Code: | a) Preparation, implementation, monitoring and inspection. b) Evaluation and studies; information and communication. |
| ### Activity title: | # Technical Assistance |
| ### Overall Objective: | To meet the eligible costs of the Managing Authority and the Monitoring Committee in managing, implementing and monitoring and control of the Programme. To meet the wider costs of effective ESF administration in Ireland, including those of the ESF Certifying Authority and Audit Authority. To meet the costs of providing technical support for the effective implementation of other activities including Transnational activities in the OP |
| ### Certifying Authority: | ESF Certifying Authority |
| Managing Authority: | ESF Managing Authority |
| Intermediate Body: | N/A |
| # Intended Beneficiaries: | Department of Enterprise, Trade and Employment (for OP Managing Authority, ESF Certifying Authority & Audit Authority (ESF Financial Control Unit)), OP Monitoring Committee, other Implementing Bodies in the OP requiring technical support. |
| # EU Co-financing Rate: | 50% |

1. CONTEXT/ PROBLEM/ NEED:

The purpose of the Technical Assistance Priority is to support the utilisation of the European Social Funds as defined in the Regulations and the Human Capital Investment Operational Programme. The Technical Assistance Priority will finance the preparation, monitoring, administrative and technical support, evaluation, audit and inspection necessary for implementing the ESF Regulations.

2. OBJECTIVES OF THE ACTIVITY:

The Technical Assistance Priority will cover certain costs in relation to the following areas of activity: - Audit Authority (ESF Financial Control Unit, DETE), - Monitoring Committee Meetings, - Management, monitoring, implementation and control of the OP, - Evaluations (including Mid-Term Evaluation) and activity level/thematic evaluations, - Seminars, - The computer based integrated data management system, - Information and publicity, document printing and other costs, - Transnational activities, - Capacity building for organizations involved in administrating ESF programmes - Retention and storage of records for the current and previous OP’s as necessary - Participation in ESF-related for a nationally and at EU level

3. ESF FUNDED ELEMENT OF ACTIVITY:

4. RESPONSIBILITIES OF INTERMEDIATE BODY/BENEFICIARY BODY:

- N/a

| 5. CONTRIBUTION TO HORIZONTAL THEMES |  |
| --- | --- |
| # A. Social Inclusion | N/A |
| B. Gender Equality & Wider Equality Opportunities | N/A |
| C. Sustainable Development | The Department of the Environment, Heritage and Local Government will be invited to become a member of the OP Monitoring Committee The MA will report on Sustainable Development as an element of the Annual Implementation Report A thematic presentation and discussion on sustainable development issues will be made to the Monitoring Committee on an annual basis Evaluation of the OP impact in relation to sustainable development will be undertaken as an element of the proposed mid term evaluation of the OP |

| 6. PERFORMANCE INDICATORS: |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Indicators: Not Applicable |  |  |  |  |  |  |  |  |  |  |
| OUTPUT |  |  |  |  |  |  |  |  |  |  |
| RESULT |  |  |  |  |  |  |  |  |  |  |
| IMPACT |  |  |  |  |  |  |  |  |  |  |

See end of document for ANNEX XX111 from Implementing Regulation 1828 of 2006

| 7. FINANCIAL INPUT |  |  |  |
| --- | --- | --- | --- |
| Budget (€/m.) | SAE €1.5 | BMW €1.5 | NAT €3.0 |
| EU Intervention Field Code | ###### 85 & 86 |  |  |
| ###### ESF Contribution €m | ###### €1.5m. |  |  |
| # Treatment of ESF | Funding for ESF-eligible activity is advanced from public funds by the Department of Enterprise, Trade and Employment. On receipt of ESF payments, receipts are lodged to the original source of funding. |  |  |
| National Co-Financing Basis (Net/Gross) | D/ETE: Gross – i.e. the Department of Enterprise, Trade and Employment provides both the ESF contribution and match funding in advance and recoups the appropriate ESF amount. Non Co-Financed expenditure, where appropriate, is also provided by the Department of Enterprise, Trade and Employment. |  |  |
| Max. ESF Co-Financing % | 50% |  |  |
| Max. Total Public Support % | 100% |  |  |
| Exch. Vote& S/Head | D/ETE Vote 34, Sub-Head M3 |  |  |
| Description of Financial Flows | ESF claims are made on the basis of vouched expenditure by the Department of Enterprise, Trade and Employment. ESF Payments made by the European Commission to Department of Enterprise, Trade and Employment through designated account at Central Bank. ESF payments distributed by ESF Paying Authority as appropriate. |  |  |

| ###### 8. FINANCIAL MANAGEMENT |  |
| --- | --- |
| Certifying Authority | ESF Certifying Authority |
| Managing Authority | HCI-OP Managing Authority |
| Intermediate Body | N/A |
| # Beneficiaries | D/ETE |
| # Nature of Support | Financial support for technical assistance |
| # Operation of Scheme | Duration of OP |
| Implementation Arrangements (Sub-Contracting?) | This activity will be implemented by the Department of Enterprise, Trade and Employment (OP Managing Authority). Sub-contracting will apply where appropriate on the basis of competitive tendering and transparent selection process. |

| ###### 9. PAYMENT ROLES |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ex-Ante Expenditure Verification checks (Art.13) by: | # Certified Claims Submitted by: | Submitted To: | Ex-Post Audit of Operations by: | System Audits By: |
| Implementing Bodies in accordance with Procedures Manuals | Implementing Bodies approved for support | OP Managing Authority DETE | ESF Fin Control Unit, D/ETE | Internal Audit D/ETE |
| EO/HEO Managing Authority DETE | HEO/AP Managing Authority DETE | Certifying Authority DETE | ESF Fin Control Unit, D/ETE | Internal Audit D/ETE |
| EO/HEO Certifying Authority DETE | Certifying Authority DETE | European Commission | ESF Fin Control Unit, D/ETE | Internal Audit D/ETE |

| ###### 10. PROJECT SELECTION |  |
| --- | --- |
| Project Selection Process | No project-work as such; selection of consultants, where necessary, will be by way of competitive tendering and Selection Committee or Managing Authority approval |
| Project Selection Criteria | Competitive tendering where applicable |
| Composition of Project Selection Committee | Where applicable, requirements will be defined by Managing Authority with approval, where necessary, of Monitoring Committee |

| 11. PUBLICITY/INFORMATION PLANS |  |
| --- | --- |
| Publicity/ Information Plans for the Activity | All stationary, publications etc, originated by the OP Managing or ESF Certifying Authorities to do either with the OP generally or constituent activities will carry both EU and national Logos and suitable reference will be made to either or both sources of funding, as appropriate in line with national requirements and those of the Commission as set out in Regulation (EC) No 1828/2006. |

12. FINANCIAL PLAN FOR THE ACTIVITY

| 13. IMPLEMENTATION CONTACT |  |  |
| --- | --- | --- |
| Body: | Contact Name: | Mr. William Mc Intosh |
| Address: | ##### Phone: | - 353 1631 3120 |
|  | ##### Fax: | 353 1 631 3262 |
|  | ##### Email: | Willie_McIntosh@entemp.ie |

- [Extract from Implementing Regulation 1828 of 2006]

- Annex XXIII : Data on participants in ESF operations by priority

NUMBER OF PARTICIPANTS PER YEAR

(people entering, those leaving, carry-over from one year to the next)

- BREAKDOWN OF PARTICIPANTS BY GENDER

BREAKDOWN OF PARTICIPANTS ACCORDING TO STATUS IN THE LABOUR MARKET

–	employed (total number of employed, including self-employed)

–	self-employed

–	unemployed (total number of unemployed including long-term unemployed)

–	long-term unemployed

–	inactive persons (total number of inactive persons, including those in education, training or retirement, those having given up business, the permanently disabled, those fulfilling domestic tasks or other)

–	inactive persons in education or training

- BREAKDOWN OF PARTICIPANTS BY AGE

–	young people (15-24 years)

–	older workers (55-64 years)

BREAKDOWN OF PARTICIPANTS BY VULNERABLE GROUPS, IN ACCORDANCE WITH NATIONAL RULES

–	minorities

–	migrants

–	disabled

–	other disadvantaged people

- BREAKDOWN OF PARTICIPANTS BY EDUCATIONAL ATTAINMENT

–	Primary or lower secondary education (ISCED 1 and 2)

–	Upper secondary education (ISCED 3)

–	Post-secondary non-tertiary education (ISCED 4)

–	Tertiary education (ISCED 5 and 6)

Article 13, Reg. 1828/2006

Art. 62 (1)(b) Reg. 1083/2006

Art. 62 (1) (a) Reg. 1083/2006